-

School Improvement Planning

| School / Nursery | The Centre Playgroup |
| --- | --- |
| Learning Community |  |
| Area ELC Manager / MLO | Bernadette Haggerty |
| Head of ELC | Heather Douglas |
| School / Nursery Roll | 35 |
| Attendance Rate |  |
| Pupils affected by the poverty related attainment gap (employment, income, housing, health, access to services, education, crime), covid & other forms of poverty not listed OTHER – Pupils not in SIMD 1 & 2, not in receipt of school meals but affected by factors detailed above. |  |
| PEF allocation 24-25: NOT FOR ELC; SIMD Quintile 1 (% and Number) NOT FOR ELC. Carry Forward: NOT FOR ELC; SIMD Quintile 5 (% and Number) NOT FOR ELC. Total Allocation 24-25: NOT FOR ELC; Other NOT FOR ELC. FME (number and %) NOT FOR ELC; Total No Pupils NOT FOR ELC. |
| Grand Challenges 2023-26 (Grand challenges are the long term strategic changes you intend to achieve i.e ‘to improve attainment in literacy) - To improve children’s Achievement and progress- literacy reading strategies - To improve Connected Learning – Digital Literacy - To Improve Engagement, participation and Inclusion – outdoor resources |  |

| Challenge: (copy/paste aligned challenge) To improve children’s Achievement and progress- literacy reading strategies |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Mission : Practitioners will ensure children have frequent and planned exposure to high quality books and writing experiences. Practitioners will use literacy strategies to foster child’s emergent literacy development to help the children understand the purpose of print and to learn the mechanics of reading, building vocabulary, expanding knowledge of the world and foster a positive attitude towards literacy related activities and writing experiences. Practitioners will record using Literacy Framework trackers for Listening and talking, Reading and Writing |  |  |  |  | Costs |  |
| Commitments(sprints) | Expected Outcomes | Measures of Impact | Lead Responsibility | Target Date | Core NOT FOR ELC | PEF NOT FOR ELC |
| Use ABC and Beyond (Weitzman and Greenberg, 2010) (used by LEL’s during training) Read book – agree strategies for all staff members to use in the playroom/during story time to improve children’s emergent literacy skills, will we continue to use the same strategies? (literacy- the ability to read and write – is emerging skill that begins at birth). - OWL pg 9 (Weitzman and Greenberg, 2010) - SPARKLE pg 18-22 (Vocabulary development) - CSPAR (includes 3 read otherwise known as Interactive shared reading) – story comprehensive- pg 35-45 (Character, setting, problem, actions, resolution) - Shoot for the SSTARS pg 23-30 – vocabulary development To do - Download and print Higher Order Thinking questions - Give a copy to each new practitioner – to support interactive shared reading. | Update/refresh practitioners’ knowledge to shape practice. | Evidence – observations – practitioners becoming familiar with and using strategies during story time and book of the month. Evidence – Observations – practitioners becoming aware of and using Higher Order Thinking questions to support children’s engagement | All staff | August 25 |  |  |
| Carry out Literacy audit in playroom | To identify gaps in resources | Evidence – data – Copy of audit given to Literacy Lead to - - Identify resources which we have - Identify resources that we need – produce wish list | Christine – Literacy Champion | August/September 25 |  |  |
| Practitioners to complete Literacy for All (Reading) – self-reflection wheel | To identify gaps in knowledge which may need supported. | Evidence – Manager to ensure copies of planners, new resources ie; books to match each planner and supporting resources (puppets, soft toys, baskets etc.) These new resources will ensure children have frequent planned access to high quality story books. Do we need more? | All Staff | September Onwards 25 |  |  |
| Use LEL Literacy Planners | To improve literacy experiences for children within the establishment when listening to a story. | Evidence – Manager to ensure copies of planners, new resources ie; books to match each planner and supporting resources (puppets, soft toys, baskets etc.) These new resources will ensure children have frequent planned access to high quality story books. Do we need more? Evidence – Minutes from staff meeting. Discuss how we will use the Literacy Planners; should these story books be our books of the month ? will each practitioner select 2 storybooks and let the children in their group vote for which one should be their book of the month? When each practitioner/group selects a story book of the month should that practitioner be responsible for picking SPARKLE words etc. from the story to be shared with the next practitioner that uses the story book? CAN WE LINK THESE TO LITERACY HOME LEARNING ACTITIVITES? (QI 2.7 Partnership) Evidence – views - At the end of each month the practitioners should meet and share with each other how they have used the story planner and story book, achievements and areas that they would improve, any links to home learning. Evidence - When working with the story book each practitioner should track their progress, sparkle works etc. through elearning journals and big book, will we have a wall display? | All Staff | September 25 onwards |  |  |
| Reading engagement Look at areas in playroom used for storytelling and resources being used by practitioners during story telling time. Do we need new resources ie, soft furnishings to make these areas more comfortable for the children ? | Identify gaps and makes areas more inviting. | Evidence – observations, checklists contained within ABC and Beyond (Weitzman and Greenberg, 2010) | Christine – literacy Champion | September 25 |  |  |
| Prepare new display of strategies | Visible for all staff to refer to when needed | Evidence – Display To support practitioners to become familiar with strategies Can this be interactive ? QR codes for startagies? QR codes for online books for children ? | Christine – literacy Champion | September 25 |  |  |
| Trackers to be completed digitally. (the framework is the CfE benchmark statements) Moderation cycle = professional dialogue underpins decisions about achieved learning and next steps TRANSITION - When marking a child ‘on track’ judgements have we considered – Has a BREADTH of learning been offered and observed? Have children responded consistently well to the level of CHALLENGE? How have children demonstrated APPLICATION of what they have learned in new and unfamiliar situations? | Tracking over time will be able to see any improvements made. | Staff meeting to give all practitioners Literacy Framework and to discuss. Practitioners to download Framework to ipads for easy access to possible activities (supporting guidance) Evidence – Practitioners using frameworks and becoming more familiar with them. Children who start in 2024-2025 these trackers will be used for 2 years and then forwarded to schools at transition time. Children who have previously attended Playgroup trackers for Listening and talking should be carried on. The aim is for all children at the end of these 2 years to be on track for school. | All Staff | October 25 onwards |  |  |
| December Check Point: Evaluative Comments Due to a member of staff being on grievance leave and other staff illness some parts have taken a backseat to deal with the day to day running. |  |  |  |  |  |  |

| Challenge: (copy/paste aligned challenge) To improve Connected Learning – Digital Literacy |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Mission : Practitioners to develop the digital literacy framework and attending training provided by the LEL’s to enhance digital literacy skills and ICT capabilities. Through using the digital literacy framework staff will begin to offer high quality digital activities across the CfE. All staff to begin using digital strategies. |  |  |  |  | Costs |  |
| Commitments(sprint) | Expected Outcomes | Measures of Impact | Lead Responsibility | Target Date | Core NOT FOR ELC | PEF NOT FOR ELC |
| Self-Reflection Wheel for staff to gather evidence about staff confidence digital literacy– The same wheel will be used before starting and completion at the end of year programme to show staff progression. N.B. First Self-Reflection Wheel must be given to staff during training session and prior to delivery of first session (QI1.1: Self-evaluation for self-improvement) | Update/refresh practitioners’ knowledge to shape practice. | Establish staff confidence/knowledge in delivering digital literacy sessions to children. (evidence – data from self -reflection wheel) (triangulation) (QI1.1: Self-evaluation for self-improvement) | Elaine - Manager | August 25 |  |  |
| Staff to undertake training provided by the LEL’s on Digital Literacy and feedback to staff. | Update/refresh practitioners’ knowledge to shape practice. | evidence – data from self -evaluation) (triangulation) (QI1.1: Self-evaluation for self-improvement) | Digital Champion | Date to be determined |  |  |
| Elaine will show staff how to use the Digital frameworks for staff, Copy to be given to each practitioner for each child in their group. (the framework is the CfE benchmark statements) Elaine will check through out the year as part of moderation. Moderation cycle = professional dialogue underpins decisions about achieved learning and next steps TRANSITION - When marking a child ‘on track’ judgements have we considered – Has a BREADTH of learning been offered and observed? Have children responded consistently well to the level of CHALLENGE? How have children demonstrated APPLICATION of what they have learned in new and unfamiliar situations? | Update/refresh practitioners’ knowledge to shape practice. | Evidence – Observations – practitioners becoming familiar with Key documents. Evidence – Minutes from meeting – - What can we do to ensure we are enhancing learning through the use of digital technology? Are children encouraged to recognise a range of technologies and their purpose in the setting, at home and the local environment? Do children know how to operate simple technological equipment? | Elaine - Manager | August 25 |  |  |
| Ensure All staff are provided with Key documents: - Resiling the Ambition: Being me (Education Scotland,Online) pp78-79 - How Good is Our Early Learning and Childcare (Education Scotland, Online) pp 45-46 - What digital learning might look like (Education Scotland, online) - Features of highly effective digital learning, teaching and assessment in schools (Education Scotland, online) | Update/refresh practitioners’ knowledge to shape practice. | Evidence – Observations – practitioners becoming familiar with Key documents. Evidence – Minutes from meeting – - What can we do to ensure we are enhancing learning through the use of digital technology? Are children encouraged to recognise a range of technologies and their purpose in the setting, at home and the local environment? Do children know how to operate simple technological equipment? | Elaine - Manager | August 24 onwards |  |  |
| Staff meeting reflect on practice (Technologies) using Rolfes Reflection Cycle:- WHAT ? SO WHAT ? WHAT NEXT ? | To identify gaps in knowledge which may need supported. | Evidence – Minutes from meeting – Resource – CfE Technology/benchmark statements for technology Staff development- What ? staff reflecting on current practice. (Technology) So what ? staff identifying what we are doing well and arears for improvement. What Next ? Do we need to purchase any new resources to support the improvements identified? Link with CfE/benchmarks | Manager to lead – All staff involvement | October 25 |  |  |
| Audit of resources (QI 1.5: Management of resources to promote equity) Meeting with committee to purchase new resources | Identify gaps in resources and makes areas more inviting. | Evidence – data – Leigh to complete audit list - Identify resources which we have - Identify resources that we need – produce list Complete audit list to highlight resources needed. Committee to agree what can be purchased from list (Evidence – Minutes from meeting) | Elaine - Manager | October 25 onwards |  |  |
| Staff to offer digital learning to children using the digital literacy framework to track children progress | Improved outcomes for children. | Evidence – observations; practitioners to begin using and becoming familiar with the framework to plan high quality experiences for children. | All Staff | October onwards |  |  |
| Staff to complete self-evaluation wheel (end of programme) (part of triangulation) (QI1.1: Self-evaluation for self-improvement) | To identify gaps in knowledge which may need supported. | Reflection Evidence to evaluate programme Next Steps Identified for digital literacy programme. (Evidence – completed self-evaluation wheel, next steps identified) (triangulation) | All Staff | Date to be determined |  |  |
| December Check Point: Evaluative Comments |  |  |  |  |  |  |

| Challenge: (copy/paste aligned challenge) To Improve Engagement, participation and Inclusion – outdoor resources |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Mission : Practitioners explore the use of the space and resources used in the outdoor area. Through using audits and questionnaire with all stakeholders, Manager and staff to make the best use of available resources to create, sustain and enhance a motivating environment for effective learning outdoors and improve outcomes for children. |  |  |  |  |  |  |
| Commitments(sprint) | Expected Outcomes | Measures of Impact | Lead Responsibility | Target Date | Core NOT FOR ELC | PEF NOT FOR ELC |
| Staff meeting reflect on practice (outdoors) using Rolfes Reflection Cycle:- WHAT ? SO WHAT ? WHAT NEXT ? | Update/refresh practitioners’ knowledge to shape practice. | Evidence – Minutes from meeting – Resource – outdoor area is it fit for purpose Staff development- What ? staff reflecting on current practice. (outdoors) So what ? staff identifying what we are doing well and arears for improvement. What Next ? Do we need to purchase any new resources to support the improvements identified? Link with CfE/benchmarks | Elaine – Manager | September 25 |  |  |
| Parents Questionaire reflect on practice (ourdoors) using Rolfes Reflection Cycle:- WHAT ? SO WHAT ? WHAT NEXT ? | To gain insight of parental views | Evidence – People views (parents) – questionnaire Resource – outdoor area is it fit for purpose What ? parents reflecting on current practice. (outdoors) So what ? parents identifying what we are doing well and arears for improvement. What Next ? Do we need to purchase any new resources to support the improvements identified? Link with CfE/benchmarks | Elaine – Manager | September 25 |  |  |
| Children’s questionnaire reflect on practice (outdoors) using Rolfes Reflection Cycle:- WHAT ? SO WHAT ? WHAT NEXT ? | To gain insight to children’s views | Evidence – People’s views – Childrens view Resource – outdoor area is it fit for purpose What ? Children reflecting on current practice. (outdoors) So what ? Children identifying what we are doing well and arears for improvement. What Next ? Do we need to purchase any new resources to support the improvements identified? Link with CfE/benchmarks | Elaine – Manager | September 25 |  |  |
| Audit of resources (QI 1.5: Management of resources to promote equity) Meeting with committee to purchase new resources | Identify gaps in resources and makes areas more inviting. | Evidence – data – Elaine to audit resources - Identify resources which we have - Identify resources that we need – produce list Complete audit list to highlight resources needed. Committee to agree what can be purchased from list (Evidence – Minutes from meeting) | Elaine – Manager and Committee members | October 25 |  |  |
| Staff meeting Audit of resources (QI 1.5: Management of resources to promote equity) Purchase resources Do we need to look at fundraising ? Area budget grants? Look at children’s ideas for resources ? | All staff to provide ideas to develop our outdoor area for our establishment | Evidence – Minutes from meeting Staff to provide ideas - How good is our early learning and childcare to evaluate current practice - How does this inform the development of our outdoor area? | All Staff |  |  |  |
| Children’s questionnaire reflect on practice (outdoors) using Rolfes Reflection Cycle:- WHAT ? SO WHAT ? WHAT NEXT ? | To gain insight to children’s views | Evidence – People’s views – Childrens view Resource – is the new resources fit for purpose What ? Children reflecting on new resources (outdoors) So what ? Children identifying what we are doing well and arears for improvement. What Next ? Do we need to purchase any new resources to support the improvements identified? Link with CfE/benchmarks | Elaine – Manager | Date to be determined |  |  |
| Parents’s questionnaire reflect on practice (outdoors) using Rolfes Reflection Cycle:- WHAT ? SO WHAT ? WHAT NEXT ? | To gain insight of parental views | Evidence – People’s views – Childrens view Resource – is the new resources fit for purpose What ? Children reflecting on new resources (outdoors) So what ? Children identifying what we are doing well and arears for improvement. What Next ? Do we need to purchase any new resources to support the improvements identified? Link with CfE/benchmarks | Elaine – Manager | Date to be determined |  |  |
| Staff’s questionnaire reflect on practice (outdoors) using Rolfes Reflection Cycle:- WHAT ? SO WHAT ? WHAT NEXT ? | To gain insight to staff’s views | Evidence – People’s views – Staff’s view Resource – is the new resources fit for purpose What ? Staff reflecting on new resources (outdoors) | Elaine – Manager | Date to be determined |  |  |
| December Check Point: Evaluative Comments Area Budget has been applied for to purchase new resources within the new year after a new reflections with stakeholders. |  |  |  |  |  |  |